## Slide 1: Atlas is on track. One decision remains.
ATLAS
Q4 2026 | Steering Committee | 28 Nov
Building the next-generation AI platform for a more productive enterprise
ON TRACK
Overall project health
Unchanged since Q3
Completion
72%
of scope delivered
Budget used
64%
$4.1M of $6.4M
BOTTOM LINE
MVP ships on time. GPU capacity is the one risk to a Q2 launch.
Workstream progress
% complete · status
Product
82%
On track
Engineering
74%
On track
Go-to-Market
58%
Watch
Key milestones
Sep 30
Foundation
Complete
Dec 15
MVP release
In progress
Feb 15
Public beta
Planned
TODAY
KEY RISK
Medium
GPU capacity from our third-party provider is not yet confirmed for Q1
If unresolved, the public beta slips four to six weeks
NEXT DECISION
By Dec 6
Approve a $0.6M reserve for dedicated GPU capacity
Secures the Feb 15 beta and de-risks the Q2 launch
Notes: Executive / project-management dashboard: KPI cards, progress rings, workstream bars, a milestone timeline, the key risk and the decision needed.

## Slide 2: Three workstreams. One critical dependency.
EXECUTIVE DASHBOARD
Product is ready; engineering and go-to-market converge on the beta gate.
Project Atlas — Q4 Executive Review · Illustrative demo
02 / 05
Product
82%
Validated scope and UX
Owner: Maya Chen
Engineering
74%
API, inference and hardening
Owner: Leo Martins
Go-to-Market
58%
Enablement and beta demand
Owner: Priya Shah
Shared dependency: GPU capacity must be secured before integrated beta testing.
Notes: Fictional demonstration data. Workstreams converge on a single capacity dependency.

## Slide 3: Delivery is ahead of budget consumption.
EXECUTIVE DASHBOARD
A controlled reserve can protect the beta without changing the approved envelope.
Project Atlas — Q4 Executive Review · Illustrative demo
03 / 05
$6.4M
Approved envelope
Total project funding
$4.1M
Used to date
64% of approved budget
$2.3M
Remaining
Includes a proposed $0.6M reserve
Scope delivered
72%
Budget consumed
64%
Notes: Fictional demonstration data. 72% delivery with 64% budget consumption.

## Slide 4: A narrow risk window. A practical mitigation.
EXECUTIVE DASHBOARD
Treat capacity as a sourcing decision with a clear owner and deadline.
Project Atlas — Q4 Executive Review · Illustrative demo
04 / 05
MEDIUM RISK
GPU allocation remains unconfirmed.
Exposure: public beta slips four to six weeks if supply is not secured.
Owner: Engineering + Procurement
DEC 2
Validate capacity
Confirm regional supply and performance.
DEC 6
Approve reserve
Commit $0.6M for dedicated allocation.
DEC 12
Close contract
Secure supply before the beta test gate.
Notes: Fictional demonstration data. Capacity risk has a dated mitigation plan.

## Slide 5: Approve the reserve. Protect the launch.
EXECUTIVE DASHBOARD
Decision required by December 6, 2026. Proposed release remains Q2 2027.
Project Atlas — Q4 Executive Review · Illustrative demo
05 / 05
$0.6M
Capacity reserve
Dedicated GPUs for beta and scale-up
Approval conditions
Capacity confirmed in writing
Contract stays within approved budget
Performance validated before release
Next gate: December 15 MVP release, followed by the February 15 public beta.
Notes: Fictional demonstration data. Approve a $0.6M capacity reserve by December 6.