## Slide 1: Fern launches March 18.
FERN
LAUNCH PLAN · Q1 2027 · LEADERSHIP REVIEW
Twelve weeks from private beta to public launch, with a $420K budget and three named risks.
30-DAY TARGET
50K
installs after launch
4.5 rating · 25% week-4 active
Timeline
12 weeks · Jan 4 – Mar 26
Jan 12
Private beta
Done
Feb 2
Store submission
Next
Feb 23
Press preview
Planned
Mar 18
Launch
Launch day
Apr 15
30-day review
Planned
Budget
$420K total
Paid social
$160K
Creators
$95K
PR & events
$70K
App store ads
$55K
Contingency
$40K
Risks
3 open · each has an owner
High
App Store review slips past March 1
Dana · Product
Medium
Bank-connection limits at peak sign-up
Omar · Eng
Medium
Support volume in launch week
Lena · Support
Fern — Launch plan · Illustrative demo
01 / 05
Notes: Fictional demonstration content.

## Slide 2: Twelve weeks, three teams, one launch date.
LAUNCH PLAN · TIMELINE
Fern — Launch plan · Illustrative demo
02 / 05
Store submission on February 2 is the gate: it leaves six weeks of review buffer before March 18.
January
February
March
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
Product
Private beta
Fixes and polish
Release build
Marketing
Waitlist
Creator content
Launch campaign
Support
Help center
Team training
Launch-week desk
Milestones
Feb 2 Store submission
Feb 23 Press preview
Mar 18 Launch
Every team finishes its build work by week 10, so launch week is execution only.

## Slide 3: Paid social and creators carry 61% of the budget.
LAUNCH PLAN · BUDGET
Fern — Launch plan · Illustrative demo
03 / 05
$420K across five channels. The $40K contingency is released only with approval in launch week.
Chart: 
| Paid social | Creators | PR & events | App store ads | Contingency
Budget ($K) | 160 | 95 | 70 | 55 | 40
$420K
Total launch budget
January 4 to April 15
61%
Paid social and creators
$255K of $420K
$40K
Contingency
Held until launch week

## Slide 4: Three risks. Each one has an owner and a trigger.
LAUNCH PLAN · RISKS
Fern — Launch plan · Illustrative demo
04 / 05
Reviewed every Monday. A tripped trigger goes to the launch lead within 24 hours.
High risk
App Store review slips
IMPACT
Launch date moves and paid media is wasted.
MITIGATION
Submit on Feb 2, keeping six weeks of buffer.
TRIGGER
No approval by March 1.
DK
Dana Kim · Product lead
Medium risk
Bank-connection limits
IMPACT
New users fail to link accounts in week one.
MITIGATION
Raise partner quota; queue links at peak.
TRIGGER
Link failures above 3%.
OR
Omar Reyes · Engineering
Medium risk
Launch-week support load
IMPACT
Slow replies pull the store rating down.
MITIGATION
Train six extra agents; in-app help first.
TRIGGER
First reply over 4 hours.
LN
Lena Novak · Support

## Slide 5: Approve $420K and the March 18 date by January 15.
LAUNCH PLAN · DECISION
A decision this month protects the February 2 store submission and the creator bookings behind it.
WHAT WE COMMIT TO, 30 DAYS AFTER LAUNCH
50K
app installs
4.5
average star rating in the stores
25%
of new users still active in week 4
Next review: April 15, 30 days after launch, against these three goals.
Fern — Launch plan · Illustrative demo
05 / 05